## GanttChart
Week For
Task | Point of Contact | LOE | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01
1. RSB Training | Derek, Walter, Nesli, Esgi | 2 | bar: 2022-02-13
2. Initialize Web Application | Derek | 6 | bar: 2022-02-13
2.1 Setup Login Credentials | Derek | 2 | bar: 2022-02-13
2.2 Stand Up Database | Derek | 2 | bar: 2022-02-13
2.3 Hash Passwords | Derek | 2 | bar: 2022-02-13
3. Data Acquisition | Derek, Walter | 20
3.1 Identify Schema | Derek, Walter | 2 | bar: 2022-02-13
3.2 Map Dictionaries to Column Features | Derek, Walter | 2
3.3 Develop Lookup Tables | Derek | 4
3.4 Develop Foreign Keys | Derek | 4
3.5 Develop Constraints | Derek | 4
3.6 Finalize Data Dictionary | Derek, Walter | 1
3.7 Deploy Database on MySQL Server | Derek | 3
4. Model Building | Walter, Nesli, Esgi | 100 | bar: 2022-02-27 to 2022-04-03
4.1 Build Logistic Model | Walter, Nesli, Esgi | 50 | bar: 2022-02-27 to 2022-04-03
4.2 Build Random Forest | Walter, Nesli, Esgi | 50 | bar: 2022-02-27 to 2022-04-03
5. Deploy Web Application | Derek | 50 | bar: 2022-02-27 to 2022-04-03
5.1 Build Plotly Dashboard | Derek | 20 | bar: 2022-02-27
5.2 Develop Insert Forms for Model Interaction | Derek | 10 | bar: 2022-04-03
5.3 Tie Insert Forms to Model with Pickle | Derek | 15 | bar: 2022-04-10 to 2022-04-17