## GanttChart
Week For
Task | Point of Contact | LOE | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01
1. RSB Training | Derek, Walter, Nesli, Esgi | 2
2. Data Acquisition | Derek, Nesli, Walter
2.1 Setup Web Application | Derek, Nesli | 10
2.2 Configure Python Batch Upload Scripts | Derek, Nesli | 5
2.3 Write MySQL Scripts (FK, PK, Cascade) | Derek, Nesli | 5
2.4 Deploy Elementary Web Application | Derek, Nesli | 5
2.5 Complete Data Dictionary | Walter | 5
3. Complete Project Charter | Esgi | 10