## Slide 1: URMC: Ventilator Allocation
22 February 2022

## Slide 2: Gantt Chart Review

## Slide 3: Objectives

## Slide 4: Upcoming Objectives
Reduce Race, Ethnicity, Insurance granularity
Acquire Charter Approval
Build SQL database
Identify relationship between COVID table and repeated encounters
Build Dashboard

## Slide 5: Achievements

## Slide 6: Achievements
Completed data security training
Acquired data
Completed Charter Draft
  Pending Approval
Built Data Model
Stood up web interface

## Slide 7: Challenges

## Slide 8: Challenges
Poor foreign key relationships
Too many races & insurance types
Obstacle for model integrability

## Slide 9: Next Steps

## Slide 10: Next Steps
Develop SQLLite database
1
Deploy onto SQLLite database to AWS MySQL server
2
Deploy Plolty Dashboard to AWS
3
Acquire Charter Approval
4